## Traceability Template
CMSC495 Team 3 |  |  |  | Requirements Traceability Matrix
Project Name |  | Work Request Application |  | Business Area |  | Software Development
Project Manager |  | Dave Leake |  | Software Development Lead |  | Ian Oliver
QA Lead |  | Will Tchouente |  | Target Implementation Date |  | 2021-12-14
BR# | Category/Functional Activity | Requirement Description | Priority | Business Need, Justification | Project Objective | Requested by | Specification | Design | Test Cases
REQ-001 | Mandatory | The site launches properly with all the relevant pages, features, and logo. | High | Application has to be functional for user interaction | Create Viable application | Will Tchouente | Finished | In progress | 1001
REQ-002 | Mandatory | User can interact with all work requests | High | User has to be able to achieve their goal in using the application | Create Viable application | Will Tchouente | Finished | In progress | 1002
REQ-003 | Nice to have | Session timeout implementation | Low | for security purpose session must timeout after inactivity | Create Viable application | Will Tchouente | Not started | Discontinued | 1003
REQ-004 | Mandatory | user can register/login to the site | High | User must be able to access application in order to use it | Create Viable application | Will Tchouente | Finished | In progress | 1004
REQ-005 | Mandatory | major functionalities like searching, filtering, etc work as expected | High | application must be functional | Create Viable application | Will Tchouente | Finished | In progress | 1005
REQ-006 | Should have | Site launches properly in all major browsers | Medium | Nice to have | Create Viable application | Will Tchouente | In Progress | In progress | 1006
REQ-007 | Nice to have | user satisfaction from site ease of use | Low | application has to be use friendly. | Create Viable application | Will Tchouente | In Progress | Not started | 1007
REQ-008 | Nice to have | Content of pages is properly aligned, well managed and without spelling mistakes. | Low | Nice to have | Create Viable application | Will Tchouente | In Progress | In progress | 1008